## Project Planner
Prim & Polished | [5 empty] | 6/21-6/28 | 6/28-7/7 | 7/7-7/14 | 7/14-7/21 | 7/21-7/28 | 7/28-8/2
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 32 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | Week
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
SPMP | 1 | 1 | 1 | 1 | 100%
Research Plugins | 2 | 4 | 2 | 4 | 15%
Host/Domain/WP/HTTPS | 2 | 1 | 2 | 1 | 15%
Learn How To Host With Name Cheap | 2 | 1 | 2 | 1 | 0%
Push The App To Github | 2 | 1 | 2 | 1 | 0%
Web Page Features | 3 | 1 | 3 | 1 | 0%
HTML/Design | 3 | 1 | 3 | 1 | 0%
Configure Buttons On Webpage | 3 | 1 | 3 | 1 | 0%
Plugins Implementation | 3 | 1 | 3 | 1 | 0%
Users Experience(Logins) | 3 | 1 | 3 | 1 | 0%
Table Schemes(DB) | 4 | 2 | 4 | 2 | 0%
Display updated DB To website | 4 | 2 | 4 | 2 | 0%
System Test Procedures | 5 | 2 | 5 | 2 | 0%
Project Review | 6 | 1 | 6 | 1 | 0%
Presentation Review | 6 | 1 | 6 | 1 | 0%